## Priority Plan
SOULSTREAM: MAGICK DICE — PRIORITY PRODUCTION PLAN
Ranked by Mark's Integration Needs ¦ UI → Characters → Dice → VFX
# | PHASE | ASSET BATCH | CATEGORY | # ASSETS | PRIORITY | EST. DAYS | STATUS
1 | PHASE 1: UI FIRST | Main Menu Key Art (concept + final) | UI/Backgrounds | 2 | 🔴 CRITICAL | 2 | ☐
2 |  | Shop Background (Barzarr) | UI/Backgrounds | 1 | 🔴 CRITICAL | 1 | ☐
3 |  | Core Battle Background | UI/Backgrounds | 1 | 🔴 CRITICAL | 1 | ☐
4 |  | Load Screens (4 scenes) | UI/Backgrounds | 4 | 🔴 HIGH | 2 | ☐
5 |  | Header Bar + Nav Bar UI | UI Elements | 2 | 🔴 CRITICAL | 1 | ☐
6 |  | Dice Tray Slot + Highlight Ring | UI Elements | 2 | 🔴 CRITICAL | 1 | ☐
7 |  | Cooldown Overlay + Wave Rune | UI Elements | 2 | 🔴 HIGH | 1 | ☐
8 |  | Quest/Mission Grimoire Screen | UI Screens | 1 | 🔴 HIGH | 1 | ☐
9 |  | HP/Mana/XP Bars + Currency Icons | UI Elements | 6 | 🔴 HIGH | 1 | ☐
10 |  | UI Buttons & Icons Set | UI Elements | 15 | 🔴 HIGH | 2 | ☐
11 | PHASE 2: CHARACTERS | Crooks Front Pose Sprite | Character Art | 1 | 🔴 CRITICAL | 1 | ☐
12 |  | Crooks Side + Back Pose | Character Art | 2 | 🔴 CRITICAL | 1 | ☐
13 |  | Crooks Lore Study + Notes | Research | 1 | 🔴 HIGH | 0.5 | ☐
14 |  | Boss 1-5 Designs + Icons | Boss Art | 10 | 🔴 CRITICAL | 5 | ☐
15 |  | Audi/Witch Horde Minions (5) | Enemy Art | 5 | 🔴 HIGH | 1 | ☐
16 |  | Palla/Werewolf Minions (5) | Enemy Art | 5 | 🔴 HIGH | 1 | ☐
17 |  | Shandor/Vampyr Minions (5) | Enemy Art | 5 | 🔴 HIGH | 1 | ☐
18 |  | Generic Horde Creatures (5) | Enemy Art | 5 | 🟡 MED | 1 | ☐
19 |  | Familiars (5 incl Mr. Violet) | Familiar Art | 5 | 🔴 HIGH | 3 | ☐
20 | PHASE 3: DICE & WEAPONS | Lucky Daggers (3 variants) | Weapons | 3 | 🔴 HIGH | 1 | ☐
21 |  | Standard Magick Die (D6) | Dice | 1 | 🔴 CRITICAL | 0.5 | ☐
22 |  | Elemental Dice Set (Fire/Ice/Shadow/etc) | Dice | 5 | 🔴 HIGH | 2 | ☐
23 |  | Crooks Lucky Die | Dice | 1 | 🔴 HIGH | 0.5 | ☐
24 |  | Spellcraft Dice (base + 10 faces) | Dice | 11 | 🔴 HIGH | 2 | ☐
25 |  | Supernatural Dice Designs (10+) | Dice | 10 | 🟡 MED | 2 | ☐
26 |  | Pebble Projectile Effects | Weapons/VFX | 3 | 🟡 MED | 1 | ☐
27 |  | Petsha Tarot Cards (52) | Game Assets | 52 | 🟡 MED | 5 | ☐
28 |  | Treasure Chests (30 variants) | Game Assets | 30 | 🔴 HIGH | 3 | ☐
29 | PHASE 4: VFX & EFFECTS | Spell Casting Effects (10) | VFX | 10 | 🔴 HIGH | 2 | ☐
30 |  | Spell Impact Effects (10) | VFX | 10 | 🔴 HIGH | 2 | ☐
31 |  | Magick Sigils (13 Schools) | VFX | 13 | 🟡 MED | 2 | ☐
32 |  | Status Effect Overlays (8) | VFX | 8 | 🟡 MED | 1 | ☐
33 |  | Gameplay Event VFX (dice merge/spawn/destroy) | VFX | 6 | 🟡 MED | 1 | ☐
34 | PHASE 5: 8 SYSTEMS | Dice Synergy Tutorial UI + Icons | System 1 | 8 | 🔴 HIGH | 2 | ☐
35 |  | Artifact Crafting UI + Icons (35+) | System 2 | 35 | 🔴 HIGH | 4 | ☐
36 |  | Dice Fusion UI + VFX (12+) | System 3 | 12 | 🔴 HIGH | 3 | ☐
37 |  | Deconstruction Gambling UI + VFX | System 4 | 10 | 🟡 MED | 2 | ☐
38 |  | Supernatural Dice Creation UI | System 5 | 7 | 🟡 MED | 2 | ☐
39 |  | Finding Familiars UI + Habitats | System 6 | 13 | 🟡 MED | 3 | ☐
40 |  | Creating Groves UI + Elements (45+) | System 7 | 45 | 🟢 LOW | 5 | ☐
41 |  | Schools of Magick Evolution UI (70+) | System 8 | 70 | 🟢 LOW | 6 | ☐
42 | PHASE 6: SCHOOL ASSETS | 13 School Emblems (all sizes) | Schools | 52 | 🟡 MED | 4 | ☐
43 |  | 13 School Backgrounds | Schools | 13 | 🟢 LOW | 3 | ☐
44 |  | School Banners + Borders + Bars | Schools | 39 | 🟢 LOW | 3 | ☐
45 |  | School Aura VFX (13) | Schools | 13 | 🟢 LOW | 2 | ☐
|  | TOTAL ASSETS: |  | 555 |  | 91.5

## Master Checklist
MASTER ASSET CHECKLIST — ALL SYSTEMS CONSOLIDATED
# | ASSET NAME | CATEGORY | PHASE | PRIORITY | UNITY PATH | PROMPT READY | GENERATED | STATUS
1 | Main Menu Key Art — Concept | UI/Backgrounds | Phase 1 | 🔴 CRIT | Assets/Art/UI/Backgrounds/ | ☐ | ☐ | ☐
2 | Main Menu Key Art — Final Render | UI/Backgrounds | Phase 1 | 🔴 CRIT | Assets/Art/UI/Backgrounds/ | ☐ | ☐ | ☐
3 | Shop Background (Barzarr) | UI/Backgrounds | Phase 1 | 🔴 CRIT | Assets/Art/UI/Backgrounds/ | ☐ | ☐ | ☐
4 | Core Battle Background | UI/Backgrounds | Phase 1 | 🔴 CRIT | Assets/Art/UI/Backgrounds/ | ☐ | ☐ | ☐
5 | Load Screen 1: Mancer Scene | UI/Backgrounds | Phase 1 | 🔴 HIGH | Assets/Art/UI/LoadScreens/ | ☐ | ☐ | ☐
6 | Load Screen 2: Battle Scene | UI/Backgrounds | Phase 1 | 🔴 HIGH | Assets/Art/UI/LoadScreens/ | ☐ | ☐ | ☐
7 | Load Screen 3: Faction Scene | UI/Backgrounds | Phase 1 | 🔴 HIGH | Assets/Art/UI/LoadScreens/ | ☐ | ☐ | ☐
8 | Load Screen 4: Supernatural Scene | UI/Backgrounds | Phase 1 | 🔴 HIGH | Assets/Art/UI/LoadScreens/ | ☐ | ☐ | ☐
9 | Header Bar (bone-iron + violet XP + cyan soul) | UI Elements | Phase 1 | 🔴 CRIT | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
10 | Bottom Nav Bar (4 icons) | UI Elements | Phase 1 | 🔴 CRIT | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
11 | Dice Tray Slot | UI Elements | Phase 1 | 🔴 CRIT | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
12 | Active Dice Highlight Ring | UI Elements | Phase 1 | 🔴 CRIT | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
13 | Cooldown Overlay | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
14 | Wave Indicator Rune | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
15 | Quest/Mission Grimoire Screen | UI Screens | Phase 1 | 🔴 HIGH | Assets/Art/UI/Screens/ | ☐ | ☐ | ☐
16 | HP Bar | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
17 | Mana Bar | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
18 | XP Bar | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
19 | Soul Crystal Currency Icon | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
20 | Gold/Coin Currency Icon | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
21 | Gem/Premium Currency Icon | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
22 | Play Button | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
23 | Settings Button | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
24 | Back Button | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
25 | Shop Icon (chained chest) | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
26 | Collection Icon (grimoire eye) | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
27 | Battle Icon (crossed axes/shield) | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
28 | Social Icon (linked skulls) | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
29 | Loading Bar Frame | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
30 | Loading Bar Fill Animation Layer | UI Elements | Phase 1 | 🔴 HIGH | Assets/Art/UI/Elements/ | ☐ | ☐ | ☐
31 | Crooks — Front Pose Sprite | Character | Phase 2 | 🔴 CRIT | Assets/Art/Characters/Crooks/ | ☐ | ☐ | ☐
32 | Crooks — Side Pose Sprite | Character | Phase 2 | 🔴 CRIT | Assets/Art/Characters/Crooks/ | ☐ | ☐ | ☐
33 | Crooks — Back Pose Sprite | Character | Phase 2 | 🔴 CRIT | Assets/Art/Characters/Crooks/ | ☐ | ☐ | ☐
34 | Crooks — Three-Quarter View | Character | Phase 2 | 🟡 MED | Assets/Art/Characters/Crooks/ | ☐ | ☐ | ☐
35 | Boss 1 — Full Design | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
36 | Boss 1 — Icon | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
37 | Boss 2 — Full Design | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
38 | Boss 2 — Icon | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
39 | Boss 3 — Full Design | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
40 | Boss 3 — Icon | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
41 | Boss 4 — Full Design | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
42 | Boss 4 — Icon | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
43 | Boss 5 — Full Design | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
44 | Boss 5 — Icon | Boss Art | Phase 2 | 🔴 CRIT | Assets/Art/Enemies/Bosses/ | ☐ | ☐ | ☐
45 | Audi Witch Minion 1 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
46 | Audi Witch Minion 2 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
47 | Audi Witch Minion 3 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
48 | Audi Witch Minion 4 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
49 | Audi Witch Minion 5 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
50 | Palla Werewolf Minion 1 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
51 | Palla Werewolf Minion 2 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
52 | Palla Werewolf Minion 3 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
53 | Palla Werewolf Minion 4 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
54 | Palla Werewolf Minion 5 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
55 | Shandor Vampyr Minion 1 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
56 | Shandor Vampyr Minion 2 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
57 | Shandor Vampyr Minion 3 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
58 | Shandor Vampyr Minion 4 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
59 | Shandor Vampyr Minion 5 | Enemy | Phase 2 | 🔴 HIGH | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
60 | Generic Horde 1 | Enemy | Phase 2 | 🟡 MED | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
61 | Generic Horde 2 | Enemy | Phase 2 | 🟡 MED | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
62 | Generic Horde 3 | Enemy | Phase 2 | 🟡 MED | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
63 | Generic Horde 4 | Enemy | Phase 2 | 🟡 MED | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
64 | Generic Horde 5 | Enemy | Phase 2 | 🟡 MED | Assets/Art/Enemies/Hordes/ | ☐ | ☐ | ☐
65 | Familiar: Fire Elemental | Familiar | Phase 2 | 🔴 HIGH | Assets/Art/Familiars/ | ☐ | ☐ | ☐
66 | Familiar: Shadow Cat | Familiar | Phase 2 | 🔴 HIGH | Assets/Art/Familiars/ | ☐ | ☐ | ☐
67 | Familiar: Crystal Spirit | Familiar | Phase 2 | 🔴 HIGH | Assets/Art/Familiars/ | ☐ | ☐ | ☐
68 | Familiar: Storm Hawk | Familiar | Phase 2 | 🔴 HIGH | Assets/Art/Familiars/ | ☐ | ☐ | ☐
69 | Familiar: Mr. Violet (Mascot Squirrel) | Familiar | Phase 2 | 🔴 HIGH | Assets/Art/Familiars/ | ☐ | ☐ | ☐
70 | Lucky Dagger — Classic | Weapons | Phase 3 | 🔴 HIGH | Assets/Art/Weapons/ | ☐ | ☐ | ☐
71 | Lucky Dagger — Shadow | Weapons | Phase 3 | 🔴 HIGH | Assets/Art/Weapons/ | ☐ | ☐ | ☐
72 | Lucky Dagger — Petsha Heirloom | Weapons | Phase 3 | 🔴 HIGH | Assets/Art/Weapons/ | ☐ | ☐ | ☐
73 | Standard Magick Die (D6) | Dice | Phase 3 | 🔴 CRIT | Assets/Art/Weapons/Dice/ | ☐ | ☐ | ☐
74 | Fire Element Die | Dice | Phase 3 | 🔴 HIGH | Assets/Art/Weapons/Dice/ | ☐ | ☐ | ☐
75 | Ice Element Die | Dice | Phase 3 | 🔴 HIGH | Assets/Art/Weapons/Dice/ | ☐ | ☐ | ☐
76 | Shadow Element Die | Dice | Phase 3 | 🔴 HIGH | Assets/Art/Weapons/Dice/ | ☐ | ☐ | ☐
77 | Lightning Element Die | Dice | Phase 3 | 🔴 HIGH | Assets/Art/Weapons/Dice/ | ☐ | ☐ | ☐
78 | Nature Element Die | Dice | Phase 3 | 🔴 HIGH | Assets/Art/Weapons/Dice/ | ☐ | ☐ | ☐
79 | Crooks Lucky Die (Special) | Dice | Phase 3 | 🔴 HIGH | Assets/Art/Weapons/Dice/ | ☐ | ☐ | ☐
80 | Pebble Projectile — Idle | Weapons/VFX | Phase 3 | 🟡 MED | Assets/Art/VFX/Projectiles/ | ☐ | ☐ | ☐
81 | Pebble Projectile — In Flight | Weapons/VFX | Phase 3 | 🟡 MED | Assets/Art/VFX/Projectiles/ | ☐ | ☐ | ☐
82 | Pebble Projectile — Impact | Weapons/VFX | Phase 3 | 🟡 MED | Assets/Art/VFX/Projectiles/ | ☐ | ☐ | ☐
83 | Treasure Chest — Common (x5) | Game Assets | Phase 3 | 🔴 HIGH | Assets/Art/Items/Chests/ | ☐ | ☐ | ☐
84 | Treasure Chest — Rare (x5) | Game Assets | Phase 3 | 🔴 HIGH | Assets/Art/Items/Chests/ | ☐ | ☐ | ☐
85 | Treasure Chest — Epic (x5) | Game Assets | Phase 3 | 🔴 HIGH | Assets/Art/Items/Chests/ | ☐ | ☐ | ☐
86 | Treasure Chest — Legendary (x5) | Game Assets | Phase 3 | 🔴 HIGH | Assets/Art/Items/Chests/ | ☐ | ☐ | ☐
87 | Treasure Chest — Supernatural (x5) | Game Assets | Phase 3 | 🟡 MED | Assets/Art/Items/Chests/ | ☐ | ☐ | ☐
88 | Treasure Chest — Faction Specific (x5) | Game Assets | Phase 3 | 🟡 MED | Assets/Art/Items/Chests/ | ☐ | ☐ | ☐
89 | Spell Cast VFX — Fire | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
90 | Spell Cast VFX — Ice | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
91 | Spell Cast VFX — Shadow | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
92 | Spell Cast VFX — Lightning | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
93 | Spell Cast VFX — Nature | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
94 | Spell Impact VFX — Fire | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
95 | Spell Impact VFX — Ice | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
96 | Spell Impact VFX — Shadow | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
97 | Spell Impact VFX — Lightning | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
98 | Spell Impact VFX — Nature | VFX | Phase 4 | 🔴 HIGH | Assets/Art/VFX/Spells/ | ☐ | ☐ | ☐
99 | Status: Frozen Overlay | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Status/ | ☐ | ☐ | ☐
100 | Status: Poisoned Overlay | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Status/ | ☐ | ☐ | ☐
101 | Status: Stunned Stars | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Status/ | ☐ | ☐ | ☐
102 | Status: Slowed Chains | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Status/ | ☐ | ☐ | ☐
103 | Status: Buffed Glow | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Status/ | ☐ | ☐ | ☐
104 | Status: Debuffed Shadow | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Status/ | ☐ | ☐ | ☐
105 | Status: Immune Shield | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Status/ | ☐ | ☐ | ☐
106 | Status: Sleep ZZZ | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Status/ | ☐ | ☐ | ☐
107 | Dice Merge Flash | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Gameplay/ | ☐ | ☐ | ☐
108 | Dice Spawn Effect | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Gameplay/ | ☐ | ☐ | ☐
109 | Dice Destroy Effect | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Gameplay/ | ☐ | ☐ | ☐
110 | Level Up Burst | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Gameplay/ | ☐ | ☐ | ☐
111 | Critical Hit Star | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Gameplay/ | ☐ | ☐ | ☐
112 | Mana Gain Sparkle | VFX | Phase 4 | 🟡 MED | Assets/Art/VFX/Gameplay/ | ☐ | ☐ | ☐

## 8 Systems Reference
8 GAME SYSTEMS — UI & ART REQUIREMENTS FOR MARK
1. DICE SYNERGY TUTORIAL ¦ Priority: 🔴 HIGH
TYPE | ASSET NAME | DESCRIPTION | PROMPT READY | GENERATED | STATUS
UI Screen | Tutorial Overlay | Full-screen semi-transparent tutorial layer | ☐ | ☐ | ☐
UI Screen | Synergy Chart Popup | Shows which dice work together | ☐ | ☐ | ☐
UI Screen | Counter Chart Popup | Shows which dice defeat others | ☐ | ☐ | ☐
Icon | Synergy Arrow (Green) | Connecting arrow — positive combo | ☐ | ☐ | ☐
Icon | Counter Arrow (Red) | Counter relationship indicator | ☐ | ☐ | ☐
Icon | Neutral Icon (Gray) | No special relationship | ☐ | ☐ | ☐
Animation | Synergy Glow Effect | Highlight when synergy activates | ☐ | ☐ | ☐
Animation | Counter Flash Effect | Flash when counter triggers | ☐ | ☐ | ☐
2. ARTIFACT CRAFTING ¦ Priority: 🔴 HIGH
TYPE | ASSET NAME | DESCRIPTION | PROMPT READY | GENERATED | STATUS
UI Screen | Crafting Workshop Interface | Main area with anvil/forge aesthetic | ☐ | ☐ | ☐
UI Screen | Component Inventory Panel | Grid of collected components | ☐ | ☐ | ☐
UI Screen | Recipe Book UI | Lists available artifact recipes | ☐ | ☐ | ☐
UI Screen | Crafting Progress Bar | Shows crafting completion | ☐ | ☐ | ☐
Icon Set | Component Icons (20+) | Various crafting materials | ☐ | ☐ | ☐
Icon Set | Artifact Icons (15+) | Finished artifact items | ☐ | ☐ | ☐
Animation | Crafting Spark VFX | Particles during crafting | ☐ | ☐ | ☐
Animation | Success Glow | Completion celebration effect | ☐ | ☐ | ☐
Animation | Rare Craft Rainbow | Special effect for rare crafts | ☐ | ☐ | ☐
3. DICE FUSION ¦ Priority: 🔴 HIGH
TYPE | ASSET NAME | DESCRIPTION | PROMPT READY | GENERATED | STATUS
UI Screen | Fusion Chamber Interface | Central fusion area with slots | ☐ | ☐ | ☐
UI Screen | Dice Selection Grid | Choose dice to fuse | ☐ | ☐ | ☐
UI Screen | Result Preview Panel | Shows potential outcome | ☐ | ☐ | ☐
UI Screen | Level Progress Indicator | Shows dice power level | ☐ | ☐ | ☐
Dice Variants | Level 1-5 Dice (per type) | Each dice has 5 visual upgrades | ☐ | ☐ | ☐
Animation | Fusion Merge VFX | Two dice combining effect | ☐ | ☐ | ☐
Animation | Power Up Aura | Glow showing increased power | ☐ | ☐ | ☐
Animation | Level Up Explosion | Celebration on level increase | ☐ | ☐ | ☐
Icon | Fusion Ready Indicator | Shows dice can be fused | ☐ | ☐ | ☐
4. DECONSTRUCTION GAMBLING ¦ Priority: 🟡 MED
TYPE | ASSET NAME | DESCRIPTION | PROMPT READY | GENERATED | STATUS
UI Screen | Deconstruction Table | Sacrifice dice interface | ☐ | ☐ | ☐
UI Screen | Gambling Wheel/Slots | Random reward spinner | ☐ | ☐ | ☐
UI Screen | Results Popup | Shows what you won | ☐ | ☐ | ☐
UI Screen | Odds Display | Shows rarity chances | ☐ | ☐ | ☐
Animation | Dice Break Apart VFX | Deconstruction animation | ☐ | ☐ | ☐
Animation | Slot Machine Spin | Wheel spinning effect | ☐ | ☐ | ☐
Animation | Jackpot Explosion | Rare/Unique win celebration | ☐ | ☐ | ☐
Animation | Common Drop (subtle) | Basic reward effect | ☐ | ☐ | ☐
Icon | Rarity Tier Icons | Common/Rare/Epic/Unique badges | ☐ | ☐ | ☐
Icon | Currency Icons | Essence, shards, etc. | ☐ | ☐ | ☐
5. SUPERNATURAL DICE CREATION ¦ Priority: 🟡 MED
TYPE | ASSET NAME | DESCRIPTION | PROMPT READY | GENERATED | STATUS
UI Screen | Ritual Chamber Interface | Dark mystical creation space | ☐ | ☐ | ☐
UI Screen | Ingredient Slot Ring | Circular slots for components | ☐ | ☐ | ☐
UI Screen | Supernatural Dice Gallery | Collection display | ☐ | ☐ | ☐
Dice Designs | Supernatural Dice Set (10+) | Unique powerful visuals | ☐ | ☐ | ☐
Animation | Ritual Circle Activation | Glowing magic circle | ☐ | ☐ | ☐
Animation | Supernatural Birth VFX | Dice emerging from ritual | ☐ | ☐ | ☐
Background | Ritual Chamber BG | Dark atmospheric background | ☐ | ☐ | ☐
6. FINDING FAMILIARS ¦ Priority: 🟡 MED
TYPE | ASSET NAME | DESCRIPTION | PROMPT READY | GENERATED | STATUS
UI Screen | Familiar Discovery Map | World map with habitats | ☐ | ☐ | ☐
UI Screen | Companion Roster | Grid of collected familiars | ☐ | ☐ | ☐
UI Screen | Familiar Detail Card | Stats and abilities display | ☐ | ☐ | ☐
Character Art | Familiar Designs (5+) | Mr. Violet, Fire Elemental, etc. | ☐ | ☐ | ☐
Character Art | Familiar Habitat Icons | Forest, cave, volcano, etc. | ☐ | ☐ | ☐
Animation | Discovery Sparkle | Finding a new familiar | ☐ | ☐ | ☐
Animation | Familiar Bond VFX | Bonding animation | ☐ | ☐ | ☐
Background | Habitat Scenes (5+) | Environment backgrounds | ☐ | ☐ | ☐
7. CREATING GROVES ¦ Priority: 🟢 LOW
TYPE | ASSET NAME | DESCRIPTION | PROMPT READY | GENERATED | STATUS
UI Screen | Grove Builder Interface | Isometric/top-down builder | ☐ | ☐ | ☐
UI Screen | Element Placement Grid | Snap-to-grid placement | ☐ | ☐ | ☐
UI Screen | Grove Inventory Panel | Available items to place | ☐ | ☐ | ☐
Assets | Grove Elements (30+) | Trees, crystals, shrines, paths | ☐ | ☐ | ☐
Assets | Magical Plants (15+) | Glowing flora varieties | ☐ | ☐ | ☐
Assets | Grove Decorations | Statues, fountains, orbs | ☐ | ☐ | ☐
Animation | Growth Animation | Plants growing when placed | ☐ | ☐ | ☐
Animation | Grove Magic Pulse | Ambient magical effect | ☐ | ☐ | ☐
Background | Grove Base Templates | Starting grove layouts | ☐ | ☐ | ☐
8. SCHOOLS OF MAGICK EVOLUTION ¦ Priority: 🟢 LOW
TYPE | ASSET NAME | DESCRIPTION | PROMPT READY | GENERATED | STATUS
UI Screen | School Selection Hub | 13 school emblems | ☐ | ☐ | ☐
UI Screen | Evolution Skill Tree | Branching upgrade paths | ☐ | ☐ | ☐
UI Screen | Mastery Progress Panel | XP and level tracking | ☐ | ☐ | ☐
Icon Set | 13 School Emblems | All schools of magick | ☐ | ☐ | ☐
Icon Set | Skill Node Icons (40+) | Individual abilities | ☐ | ☐ | ☐
Icon Set | Mastery Badges (39) | Bronze/Silver/Gold per school | ☐ | ☐ | ☐
Animation | Evolution Unlock VFX | Skill unlocked effect | ☐ | ☐ | ☐
Animation | Mastery Achievement | Level-up celebration | ☐ | ☐ | ☐
Animation | School Aura Effects | Ambient magic per school | ☐ | ☐ | ☐
Background | 13 School Backgrounds | Themed environments | ☐ | ☐ | ☐

## Daily Tracker
DAILY MOTIVATION & PROGRESS TRACKER
GEO'S VISION: Pay off the game. 100% focus on finishing. Create game-ready Unity assets.
DATE | HOURS WORKED | TOP ACCOMPLISHMENT | BLOCKERS | TOMORROW'S PRIORITY | PHASE